## Sheet1
Task | Evidence | Task Owner | Task Deadline | Task Status | Actions/Notes/Updates
Education
To create a Clean Sport Strategy approved by UKAD and the RFL Board (the Strategy must comply with the WADA International Standard for Education along with the minimum requirements set by UKAD) | 1. TBC | REDACTED | 2020-06-01 | In progress | 1. Strategy currently being fianlised in conjunction with Comms Team. 3 page plan with vision and mission.
To annually create, implement and report progress against a Clean Sport Implementation Plan approved by UKAD, working towards the objectives of the Strategy | 1. Document drafted as per this paper | REDACTED | 2020-06-01 | Completed
To maintain accurate records of attendance at/completion of anti-doping education by Players and Athlete Support Personnel and make these records available to UKAD electronically on request (details should include when, where and by whom Players were tested.) | 1. Face to face courses education courses run by REDACTED (Championship and League 1) and REDACTED (Super League). 2. RFL has fed to REDACTED directly to ensure course content is appropriate. Both have received UKAD Educator training. 3. Clubs advised at start of season of need to book on course. Clubs contact REDACTED directly to book on course. 4. RFL pays REDACTED directly and ensures cost recovery direct from Clubs (full recovery at SL level/50% for Championship/League 1) 5. Clubs advise RFL that course has been undertaken. 6. REDACTED maintain register of individuals who were present for course. 7. Database created by REDACTED on Sport TG to record which Clubs and importantly which individuals have received the training, when and where. Clubs who do not book are picked up in August and fined through Compliance department. 8. Webinar to be created to capture individuals who don't receive training. Those who don't attend face to face training (for whatever reason) must attend webinar) | REDACTED | 2020-06-01 | In progress | 1. Limited uptake this season due to virus 2. Advise Operational Rule amend in future to say that Clubs have to do it. 3. Create webinar 4. Separate Community project to also be considered
Ensure an appropriate level of training is delivered to Players in the Community game. | 1. Messages on website available to all. 2. Anti-Doping Booklet available and can be distributed | REDACTED | 2020-06-01 | In progress | 1. REDACTED has provided re-vamped version of Booklet 2. Further work being done to ensure deliver of training at community level. 3. Ensure roll-out of tick box to ensure that all Players at community level have signed up to Anti-Doping Rules - plus co-ordinate this at same time as an online course.
All Club staff to receive UKAD “Advisor” training | REDACTED to advise which staff require training in line with Operational Rules Qualifications Appendix C. | REDACTED | 2020-06-01 | In progress
To confirm that the RFL has complied with the Clean Games Policy, if applicable | 1. n/a
Communications
To provide the following information on the NGB website: 1. Anti-Doping Rules 2. Link to UKAD and International Federation website 3. Anti-Doping Rule violations 4. Link to Prohibited List 5. Strict Liability 6. Medication advice (link to Global DRO) 7. Supplement Advice 8. Testing process 9. How a Player can apply for a TUE and whether to apply in advance 10. How an individual can report possible doping | 1. On website 2. On website - check 3. On website 4. On website 5. On website 6. On website 7. On website 8. On website 9. On website 10. On website | REDACTED | 2020-04-01 | In progress | 1. Confirm international federation information has been uploaded
To evidence that: 1. as a minimum all Players and Athlete Support Personnel on the Performance Pathway are advised annually of the Prohibited List changes 2. where applicable all Players required to apply in advance for a TUE are advised annually of their responsibilities and the potential consequences of failing to meet them. | 1. 2. (i) The need for a TUE is flagged on the RFL website (ii) The presentations by REDACTED also refer to the need for TUE's. (iii) Also referred to on Hive course | REDACTED | 2020-06-01 | In progress | 1. (i) To discuss with REDACTED re how to educate international Academy players (ii) I Play Clean - make use of this resource 2. (i) Refer to UKAD on how to do this and also discuss with Ops re how to feed this into registration process.
To demonstrate commitment to clean sport through regular, pro-active communications on anti-doping (e.g. Clean Sport Week, newsletter, social media) | 1. See separate Comms Plan | REDACTED | 2020-06-01 | In progress | REDACTED is progressing.
Testing
REDACTED
Intelligence and Investigations
REDACTED
Legal
REDACTED
Governance
REDACTED
Other
REDACTED